## Infra Provisioning
Task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | day 8 | Day 9 | Day 10 | Day 11 | day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | day 23
Network Setup | bar: Day 1
Setup VPC's prod and Non-prod | bar: Day 1
Setup Subnets | bar: Day 1
Setup Routes | bar: Day 1
Setup NAT Gateway | bar: Day 1
Create Security Groups | bar: Day 1
Enable VPC Flow logs | bar: Day 1
IAM role for VPC Flowlogs | bar: Day 1
Setup VPC peering from non prod to prod | bar: Day 1
Setup OpenVPN Server | bar: Day 1
Setup AWS Secrets for staging
Create secret vault to store the sensetive environment variables for backend app | bar: Day 2 to Day 3
ECS Service Setup for Staging
Create a ALB for staging service | bar: Day 2 to Day 3
Create a ECS cluster for staging | bar: Day 2 to Day 3
Create ECR for staging service | bar: Day 2 to Day 3
Setup lifecycle rule and auto scaning process on ECR | bar: Day 2 to Day 3
Build a docker container image and push it to ECR | bar: Day 2 to Day 3
Create task definition of backend staging service | bar: Day 2 to Day 3
Create an ECS service to run the backend | bar: Day 2 to Day 3
Update the frontend application to use new ECS service for test purpose | bar: Day 2 to Day 3
Change the DNS of the application to point to new endpoints | bar: Day 2 to Day 3
Test the application | bar: Day 2 to Day 3
Staging database migration to new VPC | bar: Day 2 to Day 3
Create RDS in New VPC from staging DB | bar: Day 2 to Day 3
Create DB subnet Groups | bar: Day 2 to Day 3
Create Security Groups for private access | bar: Day 2 to Day 3
Setup backups | bar: Day 2 to Day 3
Setup enhanced monitoring | bar: Day 2 to Day 3
Setup cloudwatch logs for slow query, errors and general logs. | bar: Day 2 to Day 3
Check if we have to create new cloudfront for backend | bar: Day 4
Setup Redis on new VPC or migrate the existing redis to new VPC | bar: Day 4
CI-CD Pipeline for staging | bar: Day 4 to Day 5
Create GitHub Action Pipleine to deploy the backend services on ECS for staging | bar: Day 4 to Day 5
Test the pipeline and troubleshoot any issues | bar: Day 4 to Day 5
_
Test and Troubleshooting of Staging environment | bar: Day 6
Setup AWS Secrets for production | bar: Day 6 to Day 7
Create secret vault to store the sensetive environment variables for backend app | bar: Day 6 to Day 7
ECS Service Setup for production | bar: Day 6 to Day 7
Create a ECS cluster for production | bar: Day 6 to Day 7
Create ECR for production service | bar: Day 6 to Day 7
Setup lifecycle rule and auto scaning process on ECR | bar: Day 6 to Day 7
Create task definition of backend production service | bar: Day 6 to Day 7
Create an ECS service to run the backend | bar: Day 6 to Day 7
Update the frontend application to use new ECS service for test purpose | bar: Day 6 to Day 7
Change the DNS of the application to point to new endpoints | bar: Day 6 to Day 7
Test the application | bar: Day 6 to Day 7
Production database migration to new VPC | bar: Day 6 to Day 7; Day 17
Create RDS in New VPC from production DB | bar: Day 6 to Day 7
Create DB subnet Groups | bar: Day 6 to Day 7
Create Securty Groups for private access | bar: Day 6 to Day 7
Setup backups | bar: Day 6 to Day 7
Setup enhanced monitoring | bar: Day 6 to Day 7
Setup cloudwatch logs for slow query, errors and general logs. | bar: Day 6 to Day 7
CI-CD Pipeline for production | bar: day 8 to Day 9
Create GitHub Action Pipleine to deploy the backend services on ECS for produciton | bar: day 8 to Day 9
Test the pipeline and troubleshoot any issues | bar: day 8 to Day 9
Test and Troubleshooting of Production environment | bar: Day 10
Security | bar: Day 10
Setup encryption using KMS on RDS | bar: Day 10
Setup VPN and allow traffic only from VPN | bar: Day 10
Backup | bar: Day 10
Setup backup for RDS using AWS Backup | bar: Day 10
Setup PhpMyAdmin | bar: Day 10
Move existing PhpMyAdmin server to new VPC or create new server for db connectivity | bar: Day 10
Do a planned cutover to new environments | bar: Day 11
Disaster Recovery Plans (Need to discuss this)
Choose failover region
Recovery plans on RDS
Recovery plans on Beanstalk and EC2 instances
Test on RPO and RTO